## Sheet1
QA CINEMA PROJECT RISK ASSESSMENT
Isabella O'Hara
Risk matrices
| Negligible | Minor | Major | Hazardous | Catastrophic
Very Unlikely | Low | Low | Low medium | Medium | Medium
Unlikely | Low | Low Medium | Low medium | Medium | Medium HIgh
Moderate | Low | Low Medium | Medium | Medium High | Medium HIgh
Likely | Low | Low medium | Medium | Medium high | High
Very Likely | Low medium | Medium | Medium high | High | High
Risk Assessement
ID | Description | Evaluation | Response | Likelihood | Impact level | Risk level | Control measures | Date added | Date updated
1 | Can't complete project by deadline. | Application will not be fully functional (some functionality may be missing) so specification not fullfilled. | Inform assigned trainer + marker (Jordan) that project is incomplete and discuss potential options | Unlikely | Major |  | Create detailed and structured plan in JIRA. Use MoSCoW framework for setting MVP and prioritisation to reach MVP. | 2022-10-03
2 | Technical issues with any of tech stack | Cause delays in completion of project (could result in risk 1). May lead to loss of work - would have to redo parts. | Inform assigned trainer to get help if cannot resolve problem myself. | Moderate | Major |  | Ensure regularly pushing changes/edits to git so all work is saved and backed-up. Don't try to run to many different applications at once - reduce liklehood of one crashing. | 2022-10-03
3 | Lack of knowledge to complete task/user story. | Application will be missing functionality - may not run successfully. | First check my notes and QA community as answer likely to be there. If not ask trainer for help. | Moderate | Minor |  | Before starting a task/user story, read over notes on concepts involved to make sure I remember what is involved/needed to complete that task/US. | 2022-10-03
4 | Exceptions not all handelled | Flow of application will be impacted - potential termination | Excecute exception handling procedure (try-catch-finally) to prevent exception from occuring again. | Moderate | Major |  | Plan out code before writing - think about what checked exceptions could occur i.e. SQLException whenever dealing with SQL. | 2022-10-03
5 | Messed up with branching in git - some kind of data loss/failed merge etc. | Some functionality may go missing/overwritten | Checkout other branches | Unlikely// UPDATED: Moderate | Minor |  | Don’t't immediately delete branches - keep a version of that code safe so could just implement differences on the develop branch. //UPDATED: it happened - code was found again - easy to resolve | 2022-10-03
6 | Testing not thorough enough/insufficient testing - errors/bugs still present in MVP | Appication may terminate/not run correctly. MVP not reached = bad mark in project. | Run more tests on section of code not working. | Unlikely | Major |  | Ensure all code on MVP is tested to the industry standard of 80% coverage before adding any additional functionality//UPDATE: 80% unlikely to be reach - new aim of 60% - testing all domain, DAO and controller classes. | 2022-10-03
7 | Errors left in code (not related to MVP) | Certain functionality will not work. | Ensure comments are left where this is the case to make marker aware. | Very likely | Minor |  | Regularly run code so are aware of where errors/missing functionality so can make marker aware. | 2022-10-03
8 | Delivering a non-functional application | Application would not work as expected despite being complete. | Ensure that run app continuously throughout the development process | Unlikely | Major |  | Ensure that run app continuously throughout the development process | 2022-10-03
9 | Not fulfilling client MVP requirements | Client not happy with work completed as MVP not reached. | Ensure client knows asap that project would not reach MVP so as to create new plan of action. | Unlikely | Hazardous |  | Use MosCoW to prioritise MVP work and organise team/roles efficently so that MVP can be reached by deadline. | 2022-10-03
10 | Corrupted file | The file which stores all the documents and code for the project has a possibility to become corrupted due to many unavoidable reasons. | Backing up to Github, including backing up the schema so that the database is not lost either. If the database were corrupted for a working version of this application it would be much higher impact. | Unlikely | Minor |  | To minimise the risks of data corruption by backing up often.
11 | Loss of internet during the project | Losing signal for the internet is a possibility, and has happened previously during my time at QA. Would lead to inability to push to Git/to access online repository. | Always keep a local repository so code is accessible even if online. | Likely | Minor |  | To ensure that time is not wasted on internet issues and to keep both online and local repositorys.
12 | Leaking of passwords and personal data | If the project were used in a real life situation, extra steps would have to be taken to protect the customers personal data which is held in SQL. | Encryption, changing passwords often, ensuring confidential data has the right access permissions. | Unlikely | Catastropic |  | To ensure there is not a data protection breach.