## Sheet1
QA CINEMA PROJECT RISK ASSESSMENT
Isabella O'Hara | Jade Foster
Fatima Sheikhnur | Mariana Nikolova
Risk matrices
| Negligible | Minor | Major | Hazardous | Catastrophic
Very Unlikely | Low | Low | Low medium | Medium | Medium
Unlikely | Low | Low Medium | Low medium | Medium | Medium HIgh
Moderate | Low | Low Medium | Medium | Medium High | Medium HIgh
Likely | Low | Low medium | Medium | Medium high | High
Very Likely | Low medium | Medium | Medium high | High | High
Risk Assessement
ID | Description | Evaluation | Response | Likelihood | Impact level | Risk level | Control measures | Date added | Date updated
1 | Can't complete project by deadline. | Website will not be fully functional (some functionality may be missing) so specification/MVP not fullfilled. | Inform assigned trainer + marker (Jordan) that project is incomplete and discuss potential options | Unlikely | Major |  | Create detailed and structured plan in JIRA. Use MoSCoW framework for setting MVP and prioritisation to reach MVP. | 2022-10-03
2 | Technical issues with any of tech stack | Cause delays in completion of project (could result in risk 1). May lead to loss of work - would have to redo parts. | Inform rest of team of issue/bug and see if together it can be resolved. If not ask assigned trainer for help if cannot resolve problem. | Moderate | Major |  | Ensure regularly pushing changes/edits to git so all work is saved and backed-up. Don't try to run to many different applications at once - reduce liklehood of one crashing. | 2022-10-03
3 | Lack of knowledge to complete task/user story. | Application will be missing functionality - may not run successfully. | First check all notes and QA community as answer likely to be there, then ask other team members for help as they may be able to help. If not ask trainer for help. | Moderate | Minor |  | Before starting a task/user story, read over notes on concepts involved to make sure I remember what is involved/needed to complete that task/US. | 2022-10-03
4 | Exceptions not all handelled | Flow of application will be impacted - potential termination | Implement catch blocks to prevent exception from occuring again. | Moderate | Major |  | Plan out code before writing - think about what exceptions could occur i.e. when using the fetch API - needs a .catch | 2022-10-03
5 | Messed up with branching in git - some kind of data loss/failed merge etc. | Some functionality may go missing/overwritten | Checkout other branches to see if code present elsewhere. | Moderate// UPDATED: Likely | Minor |  | Don’t't immediately delete branches - keep a version of that code safe so could just implement differences on the develop branch. Set up a shared excel sheet to track what each branch is for /doing to reduce likelihood of overlap. | 2022-10-03 | 2022-10-10
6 | Testing not thorough enough/insufficient testing - errors/bugs still present in MVP | Appication may terminate/not run correctly. MVP not reached = bad mark in project. | Run more tests on section of code not working. | Unlikely | Major |  | Ensure all code on MVP is tested to the industry standard of 80% coverage before adding any additional functionality//UPDATE: 80%+ coverage reach on all back end APIs | 2022-10-03 | 2022-10-07
7 | Errors left in code (not related to MVP) | Certain functionality will not work. | Ensure comments are left where this is the case to make marker aware. | Very likely | Minor |  | Regularly run code so are aware of where errors/missing functionality so can make marker aware. | 2022-10-03
8 | Delivering a non-functional application | Application would not work as expected despite being complete. | Ensure that run app continuously throughout the development process | Unlikely | Major |  | Ensure that run app continuously throughout the development process | 2022-10-03
9 | Not fulfilling client MVP requirements | Client not happy with work completed as MVP not reached. | Ensure client knows asap that project would not reach MVP so as to create new plan of action. | Unlikely | Hazardous |  | Use MosCoW to prioritise MVP work and organise team/roles efficently so that MVP can be reached by deadline. | 2022-10-03
10 | Corrupted file | The file which stores all the documents and code for the project has a possibility to become corrupted due to many unavoidable reasons. | Backing up to Github, including backing up the schema so that the database is not lost either. If the database were corrupted for a working version of this application it would be much higher impact. | Unlikely | Minor |  | To minimise the risks of data corruption by backing up often. | 2022-10-03 | 2022-10-12
11 | Loss of internet during the project | Losing signal for the internet is a possibility, and has happened previously during my time at QA. Would lead to inability to push to Git/to access online repository. | Always keep a local repository so code is accessible even if online. | Likely | Minor |  | To ensure that time is not wasted on internet issues and to keep both online and local repositorys. | 2022-10-03 | 2022-10-12
12 | Leaking of passwords and personal data | If the project were used in a real life situation, extra steps would have to be taken to protect the customers personal data which is held in MongoDB | Encryption, changing passwords often, ensuring confidential data has the right access permissions. | Unlikely | Catastropic |  | To ensure there is not a data protection breach. | 2022-10-03 | 2022-10-12